To: 	{{RECIPIENT_NAME}}								{{PROPOSAL_DATE}}

{{RECIPIENT_COMPANY}}

Re: 	{{PROJECT_NAME}}

{{SALUTATION}}

We are pleased to present our Bid Proposal in the amount of ({{BID_TOTAL}}) for the above referenced project; based on RFP Information, provided on April 18, 2025.

Scope Included in Proposal

GENERAL WORK

- Furnish and install temporary power for the site crane, Hoist. elevators, GC construction trailers, general purpose power and lighting utilizing a temporary power shed that will need to sit next to the pad mount transformer.

  - Assumes no temporary electric heat

- Allowance of $10,000.00 included for PECO temporary power costs.

- Anmar will install additional raceways from shed to basement gear room to allow temporary to be back fed from permanent breakers when the building is energized so the PECO transformer can be removed.

- PECO Coordination and PECO incoming conduits from Electric Room to 5ft from building exterior

- Included all taxes, permits and inspections.

- AutoCAD coordination with other trades.

- Cleanup to buggies on floors that is taken to dumpster by others.

- Anmar shall provide one electrician ½ hour before normal working hours and ½ hour after normal working hours each day Monday-Friday.

- Furnish and install all excavation and concrete for our utility and underground conduit systems.  This includes electrical and communication duct banks, site electrical conduits, etc.  Housekeeping pads or generator pad are excluded.  Any vertical concrete duct banks are excluded.

- Price assumes Anmar use of tower crane for setting of switchgear and generator.

- Retail spaces to have code required temporary lighting fed with MC cable and code required fire alarm mounted on temporary buckets to pass inspection.

- No temporary heating in retail spaces.

- Retail/Restaurant spaces to be cold shell only.

- Price includes a $12 per hour/$780,000.00 concession from Local 98 that will be paid to Anmar over 3 payments throughout the duration of the project.

UNITS

- Furnish and install all branch circuit devices as necessary.  All devices shall be code compliant.

  - No kitchen plug mold.

  - No kitchen undercabinet lighting.

  - No lighting at balcony slab edges

  - No unit floor boxes are included in pricing.

  - Includes Arlington GPBK28B pedestal style doghouses for balcony receptacles.

  - All window wall receptacles to be supplied installed by window wall manufacturer.  Anmar to provide wiring within empty mullion raceway.

  - No screwless plates

  - No electric shades

- Apartments will have MC cable Aluminum Feeder Conductors.

- All concealed wiring to be MC cable and plenum FA cable as per code.

- Furnish and install (265) Apartment load centers (125A MLO) with all NEC code compliant breakers and white covers.

  - No spare breakers in load centers

- Install owner furnished Apartment Lighting Package

  - Assumes there is a pathway to feed the balcony wall sconces and that these do not need to be roughed-in the structural slab.

- Furnish and install Single Pole Switches. Jamb Switches are excluded.

- Furnish and install MS 120v Smoke Detectors (Not connected to the FA System).

  - We are only including 1 smoke for each bedroom and 1 for the common area

- Furnish and install putty packs in demising walls, as required by code.

  - Putty packs and/or caulking for sound are excluded.

- All handling of the appliances is by others.  Anmar to install cords for ranges/dryers once they are inside the units.

  - This will require Local 98 approval

  - Does not include reversing the swing of the refrigerator door.

DISTRIBUTION

- Furnish and install electrical distribution system per NEC – Allowance of $2,000,000.00 to Furnish.

  - PECO Coordination and PECO site conduit extended 5’ from building.

  - Furnish and install Substations, aluminum transformers, aluminum switchboards, aluminum buss duct, panels, Dist. Panels, Metering etc. – NETA Testing is excluded.

  - Furnish Arc Flash and Short Circuit Study.  Any cost for breaker/AIC changes required by the study are excluded.

  - Assumes empty conduits only for future retail spaces originating from 480V switchboard.

- Provide a metering system similar to Leviton MMU’s with HUBs.

  - No Metering Billing software.  Assumes Pearl has a metering company that will handle remote reading and billing of tenants.

- Furnish/install Diesel Generator (500 KW) Enclosure w/ ATS switches/fuel. – Allowance of $150,000.00 to Furnish.

  - Generator size based on diesel fire pumps

  - ADD ALT – Provide 1MW generator and Electric Fire Pumps – ADD Roughly $500,000.00

- Provide all code required grounding.

- Provide UL Lightning Protection System – Carrying 70K Allowance

  - No intermediate loop or Master Label

HVAC/PLUMBING/FP

- Furnish and install power for all Mechanical, Plumbing and Fire Protection and Elevator equipment.

  - VFD’s and/or starters are excluded from this proposal.

  - Install electric unit heaters that are supplied by others.

  - No control wiring.

  - Assumes that Fire Pumps will be diesel.  See generator add price above if they are electric

  - Approved submittals on equipment will be very time sensitive as they will affect completion of a coordination study.

BOH/PUBLIC SPACE

- Furnish and install all backboards, grounding, sleeves, etc. for Electric and Tele/Data systems.

- All concealed wiring to be MC cable and plenum FA cable as per code.

- Providing incoming telecom conduits from MDF to within 5ft from building exterior.

- Install owner furnished Lighting Package

  - Install BOH / PS lighting package.

  - No street lighting or site lighting poles included.

  - No lighting along tower top included

- Install owner supplied lighting control system

- Furnish and install fire rated sleeves through decks for our work only.

LOW VOLTAGE

- Furnish and install code compliant Voice Evac Fire Alarm system – Allowance of $425,000.00 to Furnish.

  - Furnish and install Fire Alarm fire phones per Philadelphia code.

  - Furnish and install power for all smoke dampers.

  - Fire alarm wiring shall be plenum rated cabling where applicable by code.

  - Includes Firefighter smoke control panel

  - Assumes 8 total units will be HVI.

  - No strobe loop into every unit. Only to actual HVI units which we have allowed for 8 total.

- Furnish and install Two-way communication call station in one location (Elevator lobby) per floor. – Allowance of $65,000 to Furnish

  - Call stations may be required in stair tower depending if stair tower doors will have access control.  This is not currently included.

- Provide all telecom wiring within units and public spaces – Allowance of $725,000.00 to F&I.

  - Assumes a tele-data symbol is 1-CAT 6 drop, TV’s are 1-CAT 6 and 1-RG6 and phones are 1-CAT 6

  - Assumes any WAP’s will be a CAT 6 run to a LV ring with blank cover.  WAP installed after turnover by IT staff.

  - No conduit from apartments to IT closets as Verizon/Comcast should be using their own subcontractor for this work (Innerduct).

  - Verizon/Comcast box is by others.

- Provide racks, patch panels, all plates, labels, and fiber riser between equipment.

- Assumes empty telecom conduits only for future retail spaces

- ADD ALT – Provide access control/CCTV/Intercom – ADD $375,000.00 allowance

Our Exclusions/ Qualifications/ Clarifications are as follows:

- Design Build / Engineering Cost is not included.  Anmar willing to assist BALA and Pearl in anyway possible with the completion of the design.

- DAS for Emergency 1st Responders and Cellular Booster System is excluded.

- All AV work is excluded from this proposal.

- All security work is excluded from this proposal.  See aforementioned Add Alternate price.

- Fire alarm wiring will NOT be installed in conduit, where concealed – FPLP Plenum Cable to be utilized.

- Responsibility for cost increases of major purchases due to tariffs or other unforeseen conditions is excluded.

- Utility company costs and/or charges for permanent services are excluded.

- Off-hour rigging of gear and/or generator is excluded.

- Concrete pads and housekeeping pads are excluded from this proposal.

- VFD’s are furnished by others, installed by Anmar.

- HVAC controls are furnished and installed by others and excluded from this proposal.

- This project has no provisions for any “ARRA” or US Steel requirements.

- Hoist elevators designated to move manpower/equipment for this project for the project duration until permanent elevators are operational.

- All bulk deliveries, trash removal, and portable restroom cleanouts must be done off-hours.

- Dual car hoist must only be used to move manpower/light material through building during normal working hours.

- Break times for operators must be staggered so there is always 1 hoist operational.

- Street closing permits are excluded from this proposal.

- Liquidated damages, hazardous materials, and removal of spoils are excluded from this proposal.

- Radiant floor heating work is excluded from this proposal.

- Any work associated with EV charging stations is excluded from this proposal.

- Pool controls are excluded from this proposal.

- Traffic and signaling work are excluded from this proposal.

- Existing utility re-work and relocations are excluded from this proposal.

- No attic stock.

- Leak detection equipment/material/installation are excluded. Anmar will furnish and install 120v power only.

- All work shall be performed during normal working hours 7:00am-3:30pm unless otherwise listed in this proposal.

- One electrician ½ hour before and ½ hour after M-F for Temporary Power is included.

- Anmar is 100% WBE.

ANMAR ADDITIONAL NOTES

- It will be very important to have a temporary roof at the 25th Floor or above.  That will allow electric closet risers, busway, panels, apartment finishes etc. to be installed on floors 4-25 (All of which are fed from the 24th Fl gear room) while the structure is still being completed above.

- For your notes down the road, below is what was assumed for productive standby power when we did the Arthaus:

  - 8 hoist jumps on Saturdays (1 guy for standby) – 64 OT hours

  - 3 Tower crane jumps on Saturdays (1 guy for standby) – 24 OT Hours

  - 32 additional Saturdays for tower crane/hoist purposes (2 guys for standby) – 512 OT Hours

  - Additional tickets for standby work over and above the aforementioned items – 214 OT hours

- Getting detailed look ahead schedules will be important so we can identify any areas of concern ahead of time.  Anmar will also develop our own schedule that can be shared.

- A detailed list of dates for the following will be critical to ensure we can plan accordingly

  - Phased turnover TCO dates of units and amenity spaces

  - Startup priority sequence list from HVAC/Plumbing subcontractors

  - Appliance Deliveries

  - Pour dates

- One comprehensive punch list per floor will considerably cut down the number of times we have to go back into finish spaces.  An issue we ran into at Arthaus was receiving 6 different punch lists from different sources all at different times.  I personally saw it led to damaged floors, counters, walls, etc.

- Anmar is willing to walk each month to go over our pencil copy billing to ensure it’s accurate and well explained.

- Just-in-time deliveries are important for our flow so units are not filled up with drywall and flooring.

- Anmar will need 1 day on the decks from the time the bottom mat of rod is set to mount all JB’s, sleeves and install PVC. prior to the top mat of rod being set.

- Control lines will need to be provided by others on the decks so we can pull dimensions for layout of aforementioned deck rough-in the day prior to installation.

- If the project will be on a platform like Procore or Autodesk Build, Anmar would like the ability to make published markups on the plans so we can keep the electrical drawings updated for the field personnel with regards to changes made during the submittal and RFI process.

- 500KW generator is being sized with the assumption that the fire pumps will be diesel and the elevators will be controlled via selector switch so only 1 elevator can operate at a time during a power outage.

- Anmar’s peak manpower at the Arthaus was 33 men.

If there are any questions, please feel free to call. Thank you.

Sincerely,

{{ESTIMATOR_NAME}}

{{ESTIMATOR_TITLE}}